## Sheet1
Please use this template to calculate how much in kind support your organisation will provide towards the works being carried out as part of the LMCWGS project.
The schedule of works is used to show assessors that the project has been planned and that all aspects of the work have been taken into account, and will form part of the assessment criteria. Please ensure you include all relevant steps involved in the delivery of the project, including who is responsible within the club and grant milestones where required. Information regarding grant timelines have been pre-populated for you where possible.
SCHEDULE OF WORKS
ACTIVITY | DATE | RESPONSIBILITY
eg. application for building permit submitted | 2025-08-30 | John Smith
Notification of grant outcome | 2025-08-01 | Council
Grant acceptance form submitted | no later than 31/08/2025
Obtain all relevant project documents (insurance, SWMS, licences, etc)
Submission of project documents for Council approval
Signing of funding agreement with Council
Please note that you must submit project documents for review and approval and sign the funding agreement before you can carry out any works. No works must take place until these steps have been completed.
Payment of 100% of grant | within 2 weeks of signing of funding agreement | Council
(Enter relevant project milestones here) eg: Contractor commences
(Enter relevant project milestones here)
(Enter relevant project milestones here)
(Enter relevant project milestones here)
(Enter relevant project milestones here)
(Enter relevant project milestones here)
Project completed
Submission of evaluation form (within one month of project completion)